## Slide 1
M18 Reporting
Francesco Mureddu
Marcella Bonanomi
Francesco Tognoni
The Lisbon Council

## Slide 2: Agenda
URBREATH Reporting Periods (RPs)
URBREATH M18 Reporting
  Technical Reporting
  Financial Reporting

## Slide 3: Reporting Periods (RPs)
Source: Data Sheet in GA & D1.1 Project Handbook URBREATH_D1.1-Project Management Handbook_Final.pdf
Reporting Period | Month from | Month to | Reporting type | Deadline | Payment type | Payment deadline for EC
RP1 | 1 | 18 | Periodic report | M20 | Interim payment | 90 days from receiving report
RP2 | 19 | 36 | Periodic report | M38 | Interim payment | 90 days from receiving report
RP3 | 37 | 48 | Final report | M50 | Final payment | 90 days from receiving report
The first RP ends in Month 18 (30th of June 2025). After this date, the project consortium has 60 days to prepare and submit the periodic report, which means by Month 20, 29th of August 2025.
The 2nd payment will come approximately 90 days after the submission of the periodic report. This is estimated for the end of November 2025.

## Slide 4: Reporting, Workflows & Tools
Type of report | Format | Lead in URBREATH | Who provides input | Due
Technical Report Part A contains structured tables with project information. | Part A is generated by the IT system, based on the information provided in Portal Continuous and Periodic Reporting modules. | Coordinator | All WP leaders, tasks leaders, and partners where relevant | 60 days after end reporting period
Technical Report Part B is a narrative description of the work carried out during the reporting period. | Part B needs to be uploaded as PDF on the Technical Report (Part B) screen. The template to use is available on the portal. | Coordinator | All WP leaders, tasks leaders, and partners where relevant | 
Financial Report | The individual financial statements (Annex 4 to the GA) for each Beneficiary • a summary financial statement • a certificate on the financial statements (CFS) (if threshold reached). | Coordinator | Partners ask their financial & admin departments to enter in the EC portal and provide financial status. How to complete your financial statement | 
Source: https://ec.europa.eu/info/funding-tenders/opportunities/docs/2021-2027/common/temp-form/report/periodic-report_horizon-euratom_en.pdf
The periodic report consists of the Technical Report (Part A+ Part B) and the Financial Report.

## Slide 5: How to prepare and submit it?

## Slide 6: Reporting Dissemination Activities

## Slide 7: Reporting Communication Activities

## Slide 8: First Reporting Period – Technical Report (Part B)
Reporting Period: 1 January 2024 – 30 June 2025 (18 months)
Technical Report (due 60 days after end of RP: 29 August 2025)
  Prepared by the Coordinator, with help from all the WP leaders and Task leaders.
    Outlines the work carried out (WP Leaders)
    Provides an overview of progress towards objectives (WP Leaders)
    Includes a publishable summary (Coordinator with input from WP Leaders)
    Details the implementation of action, economic and societal impact (Coordination with input WP Leaders/Task Leaders)
Templates: In the folder on Teams: “RP01 M01-M18 - Technical Report”
Timeline: Contributions from all WPs due 25 July 2025

## Slide 9: First Reporting Period – Technical Report (Part A)
Reporting period: 1 January 2024 – 30 June 2025 (18 months)
Additional input needed for:
Part A information :
  URBREATH Dissemination & Communication Register (All partners)
  KPI tracking (WP & Task Leaders)
  Risk register and contingency plan (WP & Task Leaders)
  Results overview (WP & Task Leaders)
  Standards (WP & Task Leaders)
  Datasets (WP & Task Leaders)
  IPR (WP & Task Leaders)
Timeline: Contributions from all WPs due 25 July 2025

## Slide 10: First Reporting Period – Financial Report
Reporting period: 1 January 2024 – 30 June (18 months)
Financial Report (due 60 days after end of RP: 29 August 2025)
  Summary of all the expenses incurred during the reporting period.
  Submitted directly by each beneficiary into the participant portal, once the reporting period is finished (after the 30th of June 2025).
  To help you to prepare the information in advance, please use the Internal Reporting Template which replicates the information you will be asked on the participant portal.
  We will ask you to fill out this excel and submit it to us first so that we can review your expenses and provide any help or request additional information if necessary. This will help us to reduce any issues detected by the European Commission.
Timeline: Financial forms from all partners due on 25 July 2025

## Slide 11: First Reporting Period – Financial Report Beneficiaries
Financial Report
  The costs are to be declared per categories, the relevant ones for URBREATH partners are listed below.
  Typing in the costs in Euro opens a pop-up window asking for additional information/explanations.
    Personnel Costs:
      Direct personnel costs as actual costs: Total Euro per person months per WP

## Slide 12: Financial Report – Personnel Costs
Financial report
Personnel Costs:
  Use of in-kind contribution from 3rd parties :
Costs of Subcontracting:
Needs explanation and should be checked in advance with the Coordinator (and PO)!
3rd party name | Type | Foreseen in Annex 1 | Explanation (if not foreseen) | Costs
Insert name | Free of charge / against payment | Yes / No | Insert comment | Insert amount in Euro
Description | Foreseen in Annex 1 | Foreseen in Annex 1 | Costs
Insert name | Yes / No | Insert comment | Insert amount in Euro

## Slide 13: Financial Report – Other Direct Costs
Other direct costs: Travel, meetings, workshops, training sessions, consumables, audits, other goods and services.
If costs declared are equal or less than 15% of personnel costs declared, NO need to give any detail, so please leave the table empty!
If costs declared are higher than 15% of personnel costs declared, the following table needs to be completed up to the level that the remaining costs are below 15% of personnel costs (NOT for all costs), starting from the items of highest value!
Please have a look at the tables included in the GA which are listing the planned other direct costs for all partners with a budget higher than 15%. If the reported costs were listed in these tables, you do not need to give detailed explanations but a simple reference to the GA is sufficient.
Short description | Category | Associated WP | Foreseen in Annex 1 | Explanation (if not foreseen) | Costs
Insert comment | Travel, workshop, consumables, ... | Insert WP number | Yes / No | Insert comment | Insert amount in Euro

## Slide 14: Financial Report – Other Direct Costs
Some other important things to indicate when reporting expenses under the 'Other Direct Costs' category (only if more than 15% of personnel costs and not listed in the GA):
Travel Costs: Date, destination, purpose (name of meeting, conference,…), number of people, associated WP (each travel separately)
Consumables: “Major cost items”! Start with the most expensive item (Literature, posters, outreach material, publication costs)
Workshops/Meetings: Title, date, type of costs (venue hire, catering, technical equipment hire, travel costs for speaker, costs for conference calls,…)

## Slide 15: First Reporting Period – Financial Report Beneficiaries
Financial data plus explanation of the use of resources needs to be filled in online in the EC portal!
  The data can NOT be completed by the Coordinator!
  The data can be completed by every registered participant contact.
  The final version can ONLY be submitted to the EC portal by the Financial Signatory. So, make sure you have a Financial Signatory assigned to the project.
  Please check back with the Coordinator BEFORE you formally submit your form to the EC Portal! The coordinator can have a look at the draft version (deadline: 25 July 2025).
  Access to the online form is via the EC participants portal “MP” (Manage Project) Tool, “Periodic Reporting”. This can be accessed after 30 June 2025.

## Slide 16: Others
Project Timesheets:
As per the Grant Agreement Article 20.1 (e), the time spent on the URBREATH project by staff members in all project partners must be supported by evidence. In most cases this evidence consists of monthly declarations (timesheets) signed by the staff member and their supervisor. Something new in Horizon Europe is that these declarations can take the form of days or half days spent on the URBREATH project (previously you had to report on the number of hours spent on the project).
There is no official template to be filled in, however, please find an example of a timesheet that the European Commission has provided to serve as a guide. These timesheets do not need to be handed in at present, however, they should be kept by each beneficiary, just in case an external audit is requested.

## Slide 17: Others
Some important things to consider when reporting time:
The European Commission views a working year in the following dimensions:
1,720 hours or
215 working days
8 hours per working day
No staff member can be over their 100% allocation on projects. For example, if their dedication is 70% to URBREATH, their dedication on other projects should not be more than 30%. Evidence of this may be requested should an audit occur.

## Slide 18: Others
Calculating the daily rate per staff member: Once you know how many days or half days a staff member has worked in the project during the reporting period, this should be multiplied by the daily rate of that specific staff member.
Whilst the proposal was calculated using the average person month rate, we have to report the REAL costs of staff members during the implementation phase of the project. Have a look at the European Commission presentation on Horizon Europe and hourly costs (page 16 onwards). This should give you a better idea on how to calculate this for each staff member.
Certificate on Financial Statements: Please keep in mind that any partner receiving over 430.000 EUR in total budget will have to provide a Certificate on Financial Statements (CFS) which is a type of audit at the end of the project where you will have to provide all of the supporting information. This is not needed for this 1st reporting period.

## Slide 19: First Reporting Period – Timeline
30 June 2025: End of 1st reporting period
1 July 2025: Online reporting tool open
25 July 2025: WPs contributions to the Technical Report due
25 July 2025: Financial forms (using the provided Internal Template) due
8 August 2025: Pre-final version of periodic report ready for final check by Executive Board (EB) and all WP leaders
21 August 2025/3 September: Deadline for comments by EB and WP leaders
22 – 29 August / 4 – 12 September 2025: Final edits by the Coordinator and submission

## Slide 20: Review
The PO will send the coordinator an invitation for a review, a date & place will then be set in close alignment with the PO.
During the review achievements, impact, delays, and next steps are presented, in full alignment with the reports submitted.
The PO will be supported by at least 1 external expert, previously presented to the consortium, avoiding any Conflict of Interests.
The PO can trigger an ethics check at the time of the review.
1st review expected September/October 2025.

## Slide 21: THANK YOU!